|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FY 2018/2019OHYC PROJECTSCHEDULE | July ‘18 | Aug’18  | Sept‘18 | Oct‘18 | Nov‘18 | Dec‘18 | Jan‘19 | Feb‘19 | Mar‘19 | Apr‘19 | May‘19 | June‘19 |
| Full CoalitionMeetings (10x)\* |  | NNO8/7 |  |  |  |  |  |  |  |  |  | Move to last Wed |
| GeneralCoalitionActivities\* |  | NNO8/7 |  | CAT & Communitysurveys | Communitysurveys | Communitysurveys due | Review Mission & Vision statement | Start FY20 Strategic Planning process | Reviewsurvey results | Needs & Resource Assessment | FinalizeStrategic Plan | Strategic Plan DUE 6/15 |
| ‘Key Leader’Events (2x)\* |  |  |  |  |  |  |  | School Board mtg 2/25 |  | tbd | tbd | tbd |
| RX Take-Back /Lock-Bags Event |  | NNO8/7 |  | 10/27 |  |  |  |  |  | 4/27 |  |  |
| *Not For Kids*Sticker Campaign |  | NNO8/7 |  |  |  |  |  |  |  |  |  |  |
| *Power to the Parent* Campaign |  |  |  | HalloweenHomecoming10/19–10/20 |  |  |  | SuperBowl |  | Spring Break 4/1-54/20 | Prom? | Graduation6/15 |
| Vaping PolicyAwareness |  |  |  |  |  |  |  |  |  |  |  |  |
| CommunityTruancy Board |  |  |  |  |  |  |  |  |  |  |  |  |
| CommunityTraining / Events |  | NNO8/7 |  |  |  |  |  |  | ACES 3/9ARC 3/28 |  |  |  |
| PAX *GoodBehaviorGame* Training |  |  |  |  |  |  |  |  |  |  |  | 6/27 |
| PAX *GBG*ClassroomImplementation |  |  |  |  |  |  |  |  |  |  |  |  |

SCHEDULE TBD

**Blank** spaces indicate inactive months
**Lighter** colors indicate planning phase
**Darker** colors indicate implementation
**\*** indicates required strategy category

Community-Based Process\*
Information Dissemination\*
Problem Identification & Referral
Environmental\*
Education\*