|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FY 2018/2019 OHYC PROJECT SCHEDULE | July  ‘18 | Aug  ’18 | Sept  ‘18 | Oct  ‘18 | Nov  ‘18 | Dec  ‘18 | Jan  ‘19 | Feb  ‘19 | Mar  ‘19 | Apr  ‘19 | May  ‘19 | June  ‘19 |
| Full Coalition Meetings (10x)\* |  | NNO 8/7 |  |  |  |  |  |  |  |  |  | Move to last Wed |
| General Coalition Activities\* |  | NNO 8/7 |  | CAT & Community surveys | Community surveys | Community surveys due | Review Mission & Vision statement | Start FY20 Strategic Planning process | Review survey results | Needs & Resource Assessment | Finalize Strategic Plan | Strategic Plan  DUE 6/15 |
| ‘Key Leader’ Events (2x)\* |  |  |  |  |  |  |  | School Board mtg 2/25 |  | tbd | tbd | tbd |
| RX Take-Back / Lock-Bags Event |  | NNO 8/7 |  | 10/27 |  |  |  |  |  | 4/27 |  |  |
| *Not For Kids* Sticker Campaign |  | NNO 8/7 |  |  |  |  |  |  |  |  |  |  |
| *Power to the  Parent* Campaign |  |  |  | Halloween Homecoming 10/19–10/20 |  |  |  | Super Bowl |  | Spring Break 4/1-5 4/20 | Prom? | Graduation 6/15 |
| Vaping Policy Awareness |  |  |  |  |  |  |  |  |  |  |  |  |
| Community Truancy Board |  |  |  |  |  |  |  |  |  |  |  |  |
| Community Training / Events |  | NNO 8/7 |  |  |  |  |  |  | ACES 3/9 ARC 3/28 |  |  |  |
| PAX *Good Behavior Game* Training |  |  |  |  |  |  |  |  |  |  |  | 6/27 |
| PAX *GBG* Classroom Implementation |  |  |  |  |  |  |  |  |  |  |  |  |

SCHEDULE TBD

**Blank** spaces indicate inactive months  
**Lighter** colors indicate planning phase  
**Darker** colors indicate implementation  
**\*** indicates required strategy category

Community-Based Process\*  
Information Dissemination\*  
Problem Identification & Referral  
Environmental\*  
Education\*